## Project Overview
PROCUREMENT PORTFOLIO — 3 BEDROOM FLAT (GERMAN FLOOR FOUNDATION)
Prepared by: Akintunde Teslim ¦ Project: Residential Building ¦ Location: Lagos, Nigeria ¦ Date: Q1 2025
PROJECT SCOPE & SPECIFICATIONS
Project Title: | Construction of 3-Bedroom Flat with German Floor Foundation
Building Type: | Residential Duplex — Ground Floor + 1st Floor (3 Bedrooms, 2 Sitting Rooms, Kitchen, 3 Bathrooms)
Foundation Type: | German Floor (Raft/Mat Foundation) — Suitable for Lagos soft/sandy soil conditions
Plot Size: | 600 sqm ¦ Building Footprint: ~180 sqm ¦ Total Floor Area: ~360 sqm (2 floors)
Construction Duration: | Estimated 18 months (Phase 1: Foundation + DPC = 3 months; Superstructure = 9 months; Finishing = 6 months)
Procurement Officer: | Akintunde Teslim ¦ Designation: Senior Procurement Officer
Project Sponsor: | Private Developer ¦ Budget Approval: Confirmed
Delivery Strategy: | Direct procurement + competitive tendering for major items; frame agreements with key suppliers
PROJECT BUDGET SUMMARY
MATERIALS BUDGET |  | LABOUR COST |  | PROFESSIONAL FEES |  | CONTINGENCY (10%)
63574700 |  | 0 |  | 0 |  | 6357470
₦ |  | ₦ |  | ₦ |  | ₦
GRAND TOTAL PROJECT COST (incl. Contingency) | [5 empty] | 69932170
PROCUREMENT & CONSTRUCTION PHASE PLAN
Phase | Description | Duration | Key Materials/Activities |  | Procurement Method | Status
Phase 1 | Site Preparation & Foundation (German Floor) | Month 1-3 | Excavation, Blinding concrete, BRC mesh, Foundation concrete, DPC, Backfill |  | Open Competitive Tendering | IN PROGRESS
Phase 2 | Ground Floor Superstructure | Month 4-8 | Block work, Columns, Beams, Lintel, Ring beam, Ground floor slab |  | Framework Agreement | UPCOMING
Phase 3 | First Floor Superstructure | Month 5-10 | Block work, Columns, Beams, Roof beam, Roof truss & covering |  | Framework Agreement | UPCOMING
Phase 4 | Roofing & External Works | Month 9-12 | Roof truss, Aluminum roofing, Fascia, Rain gutters, External rendering |  | Direct Procurement | UPCOMING
Phase 5 | Mechanical, Electrical & Plumbing | Month 11-15 | Plumbing, Electrical wiring, AC points, Solar system, Water tank |  | Specialist Contractors | UPCOMING
Phase 6 | Internal & External Finishing | Month 13-18 | Floor tiles, Wall tiles, Painting, Doors, Windows, Fittings, Landscaping |  | Direct + Competitive | UPCOMING

## Bill of Quantities
BILL OF QUANTITIES — MATERIALS PROCUREMENT
3-Bedroom Flat ¦ German Floor Foundation ¦ Lagos, Nigeria ¦ All costs in Nigerian Naira (₦)
TOTAL MATERIALS COST | [9 empty] | 63574700
# | Description | Unit | Qty | Unit Rate (₦) | Amount (₦) | Vendor 1 Quote (₦) | Vendor 2 Quote (₦) | Vendor 3 Quote (₦) | Selected Vendor | Savings (₦)
A. SITE PREPARATION & EXCAVATION
A1 | Site clearing and levelling (600 sqm) | sqm | 600 | 450 | 270000 | 270000 | 280000 | 265000 | Suntech Nig. Ltd | 10000
A2 | Excavation for German floor foundation (180 sqm × 0.6m deep) | m³ | 108 | 3500 | 378000 | 380000 | 405000 | 370000 | Kola Excavators | 27000
A3 | Anti-termite soil treatment | sqm | 180 | 1200 | 216000 | 218000 | 225000 | 215000 | Termiguard Nig. | 9000
A4 | Hardcore filling and compaction (150mm) | m³ | 27 | 8500 | 229500 | 232000 | 240000 | 228000 | Suntech Nig. Ltd | 10500
A5 | Blinding concrete (50mm, 1:3:6 mix, 180 sqm) | m³ | 9 | 55000 | 495000 | 500000 | 510000 | 495000 | Readymix Concrete Ng | 15000
SUBTOTAL A |  |  |  |  | 1588500 |  |  |  |  | 71500
B. GERMAN FLOOR FOUNDATION CONCRETE WORKS
B1 | BRC mesh (A393) — German floor reinforcement (180 sqm) | sheets | 30 | 85000 | 2550000 | 2580000 | 2600000 | 2550000 | Steel Baron Nig. | 50000
B2 | Mild steel rod Y16 (foundation column starters) | tonnes | 0.8 | 650000 | 520000 | 525000 | 530000 | 520000 | Dangote Steel | 10000
B3 | Mild steel rod Y12 (ring beam & tie bars) | tonnes | 0.5 | 650000 | 325000 | 328000 | 330000 | 325000 | Dangote Steel | 5000
B4 | Ready mix concrete 25N/mm² — Raft slab (180 sqm × 250mm) | m³ | 47 | 55000 | 2585000 | 2600000 | 2650000 | 2580000 | Lafarge ReadyMix | 65000
B5 | Binding wire (1kg rolls) | rolls | 25 | 2800 | 70000 | 71000 | 72000 | 70000 | Local market | 2000
B6 | Form work for ground beam edges (50mm boards) | sqm | 45 | 4500 | 202500 | 205000 | 208000 | 202000 | Timber King Abk | 5500
B7 | Damp proof membrane (DPM) 1200 gauge polythene | rolls | 12 | 18000 | 216000 | 217000 | 220000 | 215000 | BuildPro Supplies | 4000
B8 | Sand filling to floor level (after DPC) | m³ | 54 | 6500 | 351000 | 354000 | 360000 | 350000 | Kola Excavators | 9000
B9 | Damp proof course (DPC) bricks — ground level | sqm | 75 | 3500 | 262500 | 264000 | 268000 | 260000 | Premier Blocks Ltd | 5500
SUBTOTAL B |  |  |  |  | 7082000 |  |  |  |  | 156000
C. BLOCK WORK & SUPERSTRUCTURE
C1 | 9-inch hollow blocks (6-inch equivalent for foundation) | blocks | 4200 | 380 | 1596000 | 1600000 | 1620000 | 1590000 | Premier Blocks Ltd | 24000
C2 | 6-inch solid blocks (superstructure ground floor) | blocks | 3500 | 320 | 1120000 | 1125000 | 1130000 | 1120000 | Premier Blocks Ltd | 10000
C3 | 6-inch hollow blocks (superstructure 1st floor) | blocks | 2800 | 310 | 868000 | 870000 | 875000 | 865000 | Premier Blocks Ltd | 7000
C4 | Portland cement — Dangote 42.5 (bags) | bags | 650 | 7200 | 4680000 | 4700000 | 4750000 | 4680000 | Dangote Cement Dist. | 70000
C5 | Sharp sand (tipper loads — 5 tonnes each) | loads | 35 | 45000 | 1575000 | 1580000 | 1600000 | 1570000 | Lagos Sand Dealers | 25000
C6 | Granite 3/4 (coarse aggregate — tipper loads) | loads | 20 | 55000 | 1100000 | 1105000 | 1110000 | 1100000 | Apapa Quarry Ltd | 10000
C7 | Steel rod Y16 (columns and beams) | tonnes | 3.5 | 650000 | 2275000 | 2285000 | 2290000 | 2275000 | Dangote Steel | 15000
C8 | Steel rod Y12 (secondary reinforcement) | tonnes | 2 | 650000 | 1300000 | 1305000 | 1310000 | 1300000 | Dangote Steel | 10000
C9 | Steel rod Y10 (stirrups and links) | tonnes | 1 | 650000 | 650000 | 653000 | 658000 | 648000 | Dangote Steel | 8000
C10 | Steel rod Y8 (distribution bars, lintels) | tonnes | 0.8 | 650000 | 520000 | 523000 | 526000 | 520000 | Dangote Steel | 6000
C11 | Binding wire (coils) | coils | 50 | 2800 | 140000 | 141000 | 143000 | 140000 | Local market | 3000
C12 | Form work timber (2×3 and 2×6 boards) | pieces | 200 | 3500 | 700000 | 703000 | 708000 | 698000 | Timber King Abk | 8000
C13 | Plywood shuttering (18mm marine boards) | sheets | 60 | 18000 | 1080000 | 1082000 | 1090000 | 1078000 | BuildPro Supplies | 10000
C14 | Ground floor concrete slab (125mm, 180 sqm) | m³ | 22.5 | 55000 | 1237500 | 1240000 | 1250000 | 1235000 | Lafarge ReadyMix | 12500
C15 | First floor concrete slab (125mm, 180 sqm) | m³ | 22.5 | 55000 | 1237500 | 1240000 | 1250000 | 1235000 | Lafarge ReadyMix | 12500
C16 | Lintel blocks / pre-cast lintels (900mm) | pieces | 120 | 2500 | 300000 | 302000 | 305000 | 299000 | Premier Blocks Ltd | 5000
C17 | Ring beam concrete (columns top, perimeter) | m³ | 8 | 55000 | 440000 | 443000 | 445000 | 440000 | Lafarge ReadyMix | 5000
C18 | Window/door props (acrow / adjustable props) | pieces | 30 | 12000 | 360000 | 361000 | 365000 | 358000 | BuildPro Supplies | 5000
SUBTOTAL C |  |  |  |  | 21179000 |  |  |  |  | 246000
D. ROOFING WORKS
D1 | Roofing timber (2×6 rafters) | pieces | 100 | 3500 | 350000 | 350000 | 355000 | 345000 | Timber King Abk | 5000
D2 | Roofing timber (2×3 purlins) | pieces | 200 | 2200 | 440000 | 443000 | 448000 | 440000 | Timber King Abk | 8000
D3 | Aluminum long span roofing sheets (0.55mm) | sqm | 280 | 3800 | 1064000 | 1065000 | 1070000 | 1060000 | Alum Roofing Ng | 6000
D4 | Ridge cap aluminum | length | 25 | 4500 | 112500 | 113000 | 115000 | 111000 | Alum Roofing Ng | 2500
D5 | Fascia board aluminum | length | 60 | 3200 | 192000 | 193000 | 195000 | 191000 | Alum Roofing Ng | 3000
D6 | Rain gutters (PVC 100mm half-round) | length | 50 | 4200 | 210000 | 211000 | 213000 | 209000 | RoofPro Nig. | 3000
D7 | Downpipes PVC 75mm | length | 24 | 3500 | 84000 | 85000 | 87000 | 83000 | RoofPro Nig. | 3000
D8 | Roofing nails / screws (assorted) | kg | 30 | 1500 | 45000 | 46000 | 47000 | 45000 | Local market | 2000
D9 | Roof insulation board (50mm) | sqm | 280 | 2800 | 784000 | 786000 | 790000 | 782000 | BuildPro Supplies | 6000
D10 | Roof overhang soffit board (cement board) | sqm | 60 | 3500 | 210000 | 211000 | 213000 | 209000 | BuildPro Supplies | 3000
SUBTOTAL D |  |  |  |  | 3491500 |  |  |  |  | 41500
E. WINDOWS, DOORS & IRONMONGERY
E1 | Aluminium sliding windows 1200×1200mm | units | 12 | 85000 | 1020000 | 1022000 | 1025000 | 1018000 | Alumaco Nig. Ltd | 5000
E2 | Aluminium casement windows 600×900mm | units | 8 | 65000 | 520000 | 522000 | 525000 | 519000 | Alumaco Nig. Ltd | 5000
E3 | External security door (steel) — main entrance | units | 1 | 380000 | 380000 | 382000 | 385000 | 378000 | Ironmax Nig. | 5000
E4 | External security door (steel) — back entrance | units | 1 | 280000 | 280000 | 282000 | 285000 | 278000 | Ironmax Nig. | 5000
E5 | Internal flush doors (solid core, 900×2100mm) | units | 9 | 65000 | 585000 | 587000 | 590000 | 583000 | Woodcraft Nig. | 5000
E6 | Internal flush doors (bathroom, 700×2100mm) | units | 3 | 55000 | 165000 | 166000 | 168000 | 164000 | Woodcraft Nig. | 3000
E7 | Door frames (hardwood) | units | 14 | 18000 | 252000 | 253000 | 255000 | 251000 | Woodcraft Nig. | 3000
E8 | Door handles, hinges, bolts (complete sets) | sets | 14 | 8500 | 119000 | 120000 | 122000 | 118000 | Ironmax Nig. | 3000
E9 | Window burglar proof (black iron 16mm rods) | sqm | 60 | 12000 | 720000 | 722000 | 725000 | 719000 | Ironmax Nig. | 5000
E10 | Window nets / insect screens (aluminium frame) | units | 20 | 18000 | 360000 | 362000 | 365000 | 358000 | Alumaco Nig. Ltd | 5000
SUBTOTAL E |  |  |  |  | 4401000 |  |  |  |  | 44000
F. PLUMBING & WATER SUPPLY
F1 | uPVC pipes 110mm (drainage/sewer) | length | 80 | 4200 | 336000 | 337000 | 340000 | 334000 | Vanguard Pipes | 4000
F2 | uPVC pipes 75mm (drainage) | length | 60 | 3200 | 192000 | 193000 | 195000 | 191000 | Vanguard Pipes | 3000
F3 | PPR hot/cold water pipes 25mm | length | 120 | 1800 | 216000 | 217000 | 219000 | 215000 | Vanguard Pipes | 3000
F4 | PPR pipes 20mm (branch connections) | length | 80 | 1400 | 112000 | 113000 | 115000 | 111000 | Vanguard Pipes | 3000
F5 | Overhead water tank 5000L (polyethylene) | units | 1 | 185000 | 185000 | 186000 | 188000 | 183000 | Roto Tanks Nig. | 3000
F6 | Underground storage tank 10000L | units | 1 | 420000 | 420000 | 422000 | 425000 | 418000 | Roto Tanks Nig. | 5000
F7 | Water pump (0.5HP submersible + surface) | units | 2 | 85000 | 170000 | 172000 | 174000 | 170000 | Mikano Pumps | 4000
F8 | Water closet (WC) complete set — standard | units | 3 | 95000 | 285000 | 287000 | 290000 | 283000 | Sanitech Nig. | 5000
F9 | Pedestal wash hand basin complete | units | 3 | 65000 | 195000 | 197000 | 199000 | 194000 | Sanitech Nig. | 4000
F10 | Kitchen sink (stainless steel, double bowl) | units | 1 | 78000 | 78000 | 79000 | 81000 | 77000 | Sanitech Nig. | 3000
F11 | Shower set — rainfall type (chrome) | units | 3 | 45000 | 135000 | 136000 | 138000 | 133000 | Sanitech Nig. | 3000
F12 | Gate valve and stop cock (various sizes) | units | 20 | 5500 | 110000 | 111000 | 113000 | 109000 | Vanguard Pipes | 3000
F13 | Septic tank construction (manhole + soakaway rings) | sum | 1 | 280000 | 280000 | 282000 | 285000 | 278000 | Civil Works Nig. | 5000
SUBTOTAL F |  |  |  |  | 2714000 |  |  |  |  | 48000
G. ELECTRICAL INSTALLATION
G1 | 2.5mm twin & earth cables (100m drums) | drums | 8 | 58000 | 464000 | 466000 | 470000 | 462000 | Nigerchin Cables | 6000
G2 | 4mm twin & earth cables (100m drums) | drums | 4 | 95000 | 380000 | 382000 | 385000 | 378000 | Nigerchin Cables | 5000
G3 | 6mm single core cables (100m drums) | drums | 2 | 120000 | 240000 | 242000 | 244000 | 240000 | Nigerchin Cables | 4000
G4 | Conduit pipes 20mm (electrical) | length | 200 | 1200 | 240000 | 242000 | 244000 | 240000 | Nigerchin Cables | 4000
G5 | Consumer unit / distribution board (12-way) | units | 2 | 45000 | 90000 | 91000 | 93000 | 89000 | Clipsal Nigeria | 3000
G6 | MCB single pole 16A (circuit breakers) | units | 24 | 2800 | 67200 | 68000 | 69000 | 67000 | Schneider Elec. | 1800
G7 | Single socket outlets (surface/flush) | units | 40 | 3500 | 140000 | 141000 | 143000 | 139000 | Clipsal Nigeria | 3000
G8 | Double socket outlets | units | 20 | 4500 | 90000 | 91000 | 93000 | 89000 | Clipsal Nigeria | 3000
G9 | Switch plates (1-gang, 2-gang) | units | 30 | 2800 | 84000 | 85000 | 87000 | 83000 | Clipsal Nigeria | 3000
G10 | Light fittings — LED downlights 12W | units | 30 | 8500 | 255000 | 256000 | 258000 | 253000 | Philips Nigeria | 3000
G11 | Exterior wall lights (weatherproof) | units | 8 | 12000 | 96000 | 97000 | 99000 | 95000 | Philips Nigeria | 3000
G12 | Inverter + 200Ah batteries (2-unit solar system) | sets | 1 | 750000 | 750000 | 752000 | 756000 | 748000 | Victron Energy Ng | 6000
G13 | Solar panels 400W monocrystalline | units | 4 | 180000 | 720000 | 722000 | 726000 | 718000 | Jinko Solar Nig. | 6000
G14 | Earthing system (copper rods + busbar) | sum | 1 | 55000 | 55000 | 56000 | 58000 | 54000 | Nigerchin Cables | 3000
G15 | Prepaid meter + armoured cable (EKEDC connection) | sum | 1 | 125000 | 125000 | 126000 | 128000 | 123000 | EKEDC Approved | 3000
SUBTOTAL G |  |  |  |  | 3796200 |  |  |  |  | 56800
H. WALL PLASTERING & SCREEDING
H1 | Internal plastering (walls — 15mm coat) | sqm | 760 | 1800 | 1368000 | 1370000 | 1375000 | 1365000 | Buildmat Nig. | 7000
H2 | External rendering (20mm, textured finish) | sqm | 420 | 2200 | 924000 | 926000 | 930000 | 922000 | Buildmat Nig. | 6000
H3 | Floor screeding (ground floor 50mm) | sqm | 180 | 1500 | 270000 | 271000 | 273000 | 269000 | Buildmat Nig. | 3000
H4 | Floor screeding (first floor 50mm) | sqm | 180 | 1500 | 270000 | 271000 | 273000 | 269000 | Buildmat Nig. | 3000
H5 | Ceiling board (9mm POP / gyp board) | sqm | 360 | 3500 | 1260000 | 1263000 | 1268000 | 1258000 | CeilPro Nig. | 8000
H6 | Ceiling cornice & moulding | length | 200 | 1800 | 360000 | 362000 | 365000 | 358000 | CeilPro Nig. | 5000
H7 | Cement & sand (plastering work) | bags | 180 | 7200 | 1296000 | 1298000 | 1305000 | 1292000 | Dangote Cement | 9000
SUBTOTAL H |  |  |  |  | 5748000 |  |  |  |  | 41000
I. FLOOR & WALL TILING
I1 | Porcelain floor tiles 600×600mm (living areas) | sqm | 120 | 8500 | 1020000 | 1022000 | 1026000 | 1018000 | Eleganza Tiles | 6000
I2 | Ceramic floor tiles 300×300mm (bedrooms) | sqm | 90 | 5800 | 522000 | 524000 | 527000 | 521000 | Eleganza Tiles | 5000
I3 | Bathroom wall tiles 300×600mm (glazed) | sqm | 150 | 6500 | 975000 | 978000 | 982000 | 974000 | Eleganza Tiles | 7000
I4 | Kitchen wall tiles 300×600mm (glazed) | sqm | 40 | 6500 | 260000 | 261000 | 263000 | 259000 | Eleganza Tiles | 3000
I5 | Outdoor terrace tiles (anti-slip 600×600mm) | sqm | 30 | 9500 | 285000 | 286000 | 289000 | 283000 | Eleganza Tiles | 4000
I6 | Tile adhesive (25kg bags) | bags | 90 | 4800 | 432000 | 433000 | 435000 | 431000 | Weber Nigeria | 3000
I7 | Tile grout (assorted colours, 5kg packs) | packs | 40 | 2500 | 100000 | 101000 | 102000 | 100000 | Weber Nigeria | 2000
I8 | Tile spacers and trim profiles | sum | 1 | 45000 | 45000 | 46000 | 47000 | 44000 | Local market | 2000
I9 | Staircase tiles (300×600mm non-slip nosing) | sqm | 25 | 9500 | 237500 | 238000 | 240000 | 236000 | Eleganza Tiles | 2500
SUBTOTAL I |  |  |  |  | 3876500 |  |  |  |  | 34500
J. PAINTING & DECORATION
J1 | Exterior emulsion paint (anti-fungal, 20L tins) | tins | 20 | 38000 | 760000 | 762000 | 765000 | 758000 | Dulux Nigeria | 5000
J2 | Interior emulsion paint (various colours, 20L) | tins | 25 | 32000 | 800000 | 802000 | 805000 | 798000 | Dulux Nigeria | 5000
J3 | Gloss paint (doors, windows, ironwork, 5L) | tins | 15 | 12000 | 180000 | 181000 | 183000 | 179000 | Dulux Nigeria | 3000
J4 | PVA bonding agent (20L) | tins | 10 | 15000 | 150000 | 151000 | 153000 | 149000 | Sika Nigeria | 3000
J5 | Wall filler / skim coat (25kg bags) | bags | 40 | 4500 | 180000 | 181000 | 183000 | 179000 | Buildmat Nig. | 3000
J6 | Masking tape, brushes, rollers, trays (misc.) | sum | 1 | 85000 | 85000 | 86000 | 88000 | 84000 | Local market | 3000
J7 | Sandpaper assorted grits (bulk) | sum | 1 | 35000 | 35000 | 36000 | 37000 | 34000 | Local market | 2000
SUBTOTAL J |  |  |  |  | 2190000 |  |  |  |  | 24000
K. STAIRCASE & RAILINGS
K1 | Staircase steel structure (mild steel stringer) | sum | 1 | 420000 | 420000 | 422000 | 426000 | 418000 | SteelFab Nig. | 6000
K2 | Staircase tiles & finishing (see tiles above) | sum | 1 | 0 | 0 | 0 | 0 | 0 | — | 0
K3 | Stainless steel handrail (38mm tube) | length | 12 | 25000 | 300000 | 301000 | 304000 | 298000 | SteelFab Nig. | 4000
K4 | Balustrade posts stainless steel | pieces | 16 | 18000 | 288000 | 289000 | 291000 | 287000 | SteelFab Nig. | 3000
K5 | Glass balustrade panels (8mm tempered) | sqm | 8 | 85000 | 680000 | 682000 | 686000 | 678000 | GlassTech Nig. | 6000
SUBTOTAL K |  |  |  |  | 1688000 |  |  |  |  | 19000
L. EXTERNAL WORKS & LANDSCAPING
L1 | Perimeter fence (9-inch block, 3m high) | sqm | 120 | 15000 | 1800000 | 1806000 | 1812000 | 1800000 | Premier Blocks Ltd | 12000
L2 | Gate — sliding steel (4m wide) | units | 1 | 650000 | 650000 | 652000 | 656000 | 648000 | Ironmax Nig. | 6000
L3 | Pedestrian gate (steel, 1.2m) | units | 1 | 180000 | 180000 | 181000 | 183000 | 179000 | Ironmax Nig. | 3000
L4 | Paving blocks (driveway/walkway — 200sqm) | sqm | 200 | 4500 | 900000 | 902000 | 905000 | 899000 | Interloc Nig. | 5000
L5 | Exterior security lights (solar 100W floodlight) | units | 4 | 45000 | 180000 | 181000 | 183000 | 179000 | Solaris Nig. | 3000
L6 | Borehole drilling (100m depth + casing) | sum | 1 | 1200000 | 1200000 | 1202000 | 1206000 | 1198000 | Aqua Drill Nig. | 6000
L7 | Soakaway pit / soak-away rings (3 no.) | sum | 1 | 180000 | 180000 | 181000 | 183000 | 179000 | Civil Works Nig. | 3000
L8 | Site drainage channel (surface water) | length | 40 | 6500 | 260000 | 261000 | 263000 | 259000 | Civil Works Nig. | 3000
L9 | Topsoil and lawn grass (turfing) | sqm | 200 | 1500 | 300000 | 302000 | 304000 | 299000 | Green Thumb Nig. | 4000
L10 | Concrete kerb edging (driveway) | length | 50 | 3500 | 175000 | 176000 | 178000 | 174000 | Interloc Nig. | 3000
SUBTOTAL L |  |  |  |  | 5825000 |  |  |  |  | 48000
BILL OF QUANTITIES — GRAND SUMMARY
A | Site Preparation & Excavation | [8 empty] | 1588500
B | German Floor Foundation | [8 empty] | 7077000
C | Block Work & Superstructure | [8 empty] | 21179000
D | Roofing Works | [8 empty] | 3491500
E | Windows, Doors & Ironmongery | [8 empty] | 4401000
F | Plumbing & Water Supply | [8 empty] | 2714000
G | Electrical Installation | [8 empty] | 3796200
H | Wall Plastering & Screeding | [8 empty] | 5748000
I | Floor & Wall Tiling | [8 empty] | 3876500
J | Painting & Decoration | [8 empty] | 2190000
K | Staircase & Railings | [8 empty] | 1688000
L | External Works & Landscaping | [8 empty] | 5825000
GRAND TOTAL MATERIALS COST | [9 empty] | 63574700

## Labour Cost
LABOUR COST SCHEDULE — 3 BEDROOM FLAT
All costs in Nigerian Naira (₦) ¦ Based on Lagos State minimum wage rates + market premium
TOTAL LABOUR COST | [7 empty] | 49765000
# | Trade / Activity | Phase | Duration | No. of Workers | Daily Rate (₦/worker) | Total Days | Man-Days | Total Labour (₦)
SECTION A — SITE PREPARATION & FOUNDATION
L01 | Site foreman / Supervisor | Phase 1 | 18 months | 1 | 35000 | N/A | 18 | 630000
L02 | Civil/Structural Engineer (site visits) | Phase 1–3 | 18 months | 1 | 150000 | N/A | 18 | 2700000
L03 | Site clearance labourers | Phase 1 | 5 days | 8 | 3500 | 5 | 40 | 140000
L04 | Excavation gang (German floor) | Phase 1 | 10 days | 6 | 4500 | 10 | 60 | 270000
L05 | Anti-termite treatment applicator | Phase 1 | 2 days | 2 | 5000 | 2 | 4 | 20000
L06 | Hardcore laying & compaction labourers | Phase 1 | 5 days | 4 | 3500 | 5 | 20 | 70000
L07 | Blinding concrete gang (mixing & pouring) | Phase 1 | 3 days | 6 | 4000 | 3 | 18 | 72000
L08 | BRC mesh placement & binding workers | Phase 1 | 5 days | 6 | 4500 | 5 | 30 | 135000
L09 | Foundation concrete gang (raft pour) | Phase 1 | 3 days | 10 | 5000 | 3 | 30 | 150000
L10 | DPC bricklaying gang | Phase 1 | 4 days | 6 | 4500 | 4 | 24 | 108000
SUBTOTAL A — FOUNDATION LABOUR | [7 empty] | 4295000
SECTION B — SUPERSTRUCTURE & BLOCK WORK
L11 | Master bricklayer (ground floor) | Phase 2 | 30 days | 4 | 8000 | 30 | 120 | 960000
L12 | Assistant bricklayers (ground floor) | Phase 2 | 30 days | 8 | 4500 | 30 | 240 | 1080000
L13 | Master bricklayer (first floor) | Phase 3 | 30 days | 4 | 8000 | 30 | 120 | 960000
L14 | Assistant bricklayers (first floor) | Phase 3 | 30 days | 8 | 4500 | 30 | 240 | 1080000
L15 | Steel bender / fixer (columns & beams) | Phase 2–3 | 40 days | 4 | 7500 | 40 | 160 | 1200000
L16 | Form work carpenter (shuttering) | Phase 2–3 | 35 days | 4 | 7000 | 35 | 140 | 980000
L17 | Concrete gang (columns, beams, slabs) | Phase 2–3 | 20 days | 8 | 5000 | 20 | 160 | 800000
L18 | Ring beam & lintel gang | Phase 2–3 | 10 days | 6 | 5000 | 10 | 60 | 300000
SUBTOTAL B — SUPERSTRUCTURE LABOUR | [7 empty] | 7360000
SECTION C — ROOFING
L19 | Master carpenter (roof truss) | Phase 4 | 20 days | 2 | 9000 | 20 | 40 | 360000
L20 | Assistant carpenters (roof truss) | Phase 4 | 20 days | 4 | 5000 | 20 | 80 | 400000
L21 | Aluminum roofing fixers | Phase 4 | 10 days | 4 | 7000 | 10 | 40 | 280000
L22 | Fascia, gutter & downpipe fitters | Phase 4 | 5 days | 3 | 5500 | 5 | 15 | 82500
SUBTOTAL C — ROOFING LABOUR | [7 empty] | 1122500
SECTION D — PLUMBING
L23 | Licensed plumber (master) | Phase 5 | 45 days | 1 | 12000 | 45 | 45 | 540000
L24 | Plumbing assistant | Phase 5 | 45 days | 2 | 5500 | 45 | 90 | 495000
L25 | Drainage gang (external sewer) | Phase 5 | 10 days | 4 | 4500 | 10 | 40 | 180000
L26 | Water tank installation crew | Phase 5 | 3 days | 3 | 5000 | 3 | 9 | 45000
L27 | Borehole casing & pump installation | Phase 5 | 5 days | 3 | 6000 | 5 | 15 | 90000
SUBTOTAL D — PLUMBING LABOUR | [7 empty] | 1350000
SECTION E — ELECTRICAL WORKS
L28 | Licensed electrician (master) | Phase 5 | 50 days | 1 | 15000 | 50 | 50 | 750000
L29 | Electrician assistant | Phase 5 | 50 days | 2 | 6000 | 50 | 100 | 600000
L30 | Solar system installer | Phase 5 | 5 days | 2 | 12000 | 5 | 10 | 120000
L31 | EKEDC meter connection supervisor | Phase 5 | 2 days | 1 | 25000 | 2 | 2 | 50000
SUBTOTAL E — ELECTRICAL LABOUR | [7 empty] | 1520000
SECTION F — PLASTERING & SCREEDING
L32 | Master plasterer | Phase 6 | 45 days | 2 | 8500 | 45 | 90 | 765000
L33 | Plasterer assistants | Phase 6 | 45 days | 6 | 4000 | 45 | 270 | 1080000
L34 | Floor screeding gang | Phase 6 | 10 days | 4 | 5000 | 10 | 40 | 200000
L35 | POP ceiling installer | Phase 6 | 15 days | 3 | 8000 | 15 | 45 | 360000
SUBTOTAL F — PLASTERING LABOUR | [7 empty] | 2405000
SECTION G — TILING
L36 | Master tiler (floor & wall) | Phase 6 | 40 days | 2 | 10000 | 40 | 80 | 800000
L37 | Tiling assistants | Phase 6 | 40 days | 4 | 4500 | 40 | 160 | 720000
SUBTOTAL G — TILING LABOUR | [7 empty] | 1520000
SECTION H — PAINTING
L38 | Master painter | Phase 6 | 30 days | 2 | 8500 | 30 | 60 | 510000
L39 | Painter assistants | Phase 6 | 30 days | 4 | 4000 | 30 | 120 | 480000
SUBTOTAL H — PAINTING LABOUR | [7 empty] | 990000
SECTION I — STEELWORK, DOORS & WINDOWS
L40 | Steel fabricator (staircase, railing) | Phase 6 | 15 days | 2 | 10000 | 15 | 30 | 300000
L41 | Door & window fixing gang | Phase 6 | 10 days | 4 | 6000 | 10 | 40 | 240000
L42 | Glass installation crew | Phase 6 | 5 days | 3 | 8000 | 5 | 15 | 120000
SUBTOTAL I — STEELWORK LABOUR | [7 empty] | 660000
SECTION J — EXTERNAL WORKS
L43 | Fence bricklayer & assistants | Phase 6 | 20 days | 6 | 5000 | 20 | 120 | 600000
L44 | Gate fabricator & installer | Phase 6 | 5 days | 3 | 8000 | 5 | 15 | 120000
L45 | Paving block layer | Phase 6 | 15 days | 4 | 5500 | 15 | 60 | 330000
L46 | General labourer (site cleaning, misc.) | Phase 1–6 | 180 days | 2 | 3500 | 180 | 360 | 1260000
L47 | Security watchman (site) | Phase 1–6 | 540 days | 1 | 2500 | 540 | 540 | 1350000
SUBTOTAL J — EXTERNAL WORKS LABOUR | [7 empty] | 3660000
GRAND TOTAL LABOUR COST | [7 empty] | 49765000

## Supplier Analysis
SUPPLIER EVALUATION & SELECTION ANALYSIS
Weighted scoring methodology — All suppliers evaluated on 5 criteria (1–10 scale)
EVALUATION CRITERIA WEIGHTS
| Criteria | Weight
C1 | Price Competitiveness | 30% | How competitive is the quoted price vs market?
C2 | Delivery Lead Time | 20% | Can they supply on schedule — critical for construction timeline?
C3 | Product Quality / Standard | 25% | Do they meet SON, NAFDAC, or project specifications?
C4 | Financial Stability & Track Record | 15% | Are they registered, with references and financial capacity?
C5 | After-Sales / Warranty Support | 10% | Do they offer replacement, warranty, or post-supply support?
SUPPLIER SCORECARD — KEY MATERIAL CATEGORIES
CATEGORY 1: CEMENT (Dangote, Lafarge, BUA)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Dangote Cement Dist. | Ilupeju, Lagos | 9 | 8 | 9 | 8 | 7 | 8.45 | ✓ SELECTED
Lafarge Nigeria | Ikeja, Lagos | 8 | 9 | 9 | 7 | 8 | 8.3 | Not selected
BUA Cement Dealer | Mushin, Lagos | 8 | 7 | 8 | 8 | 6 | 7.6 | Not selected
RATIONALE: Highest weighted score (8.55). Best price competitiveness and quality consistency. Framework agreement for 650 bags secured at ₦7,200/bag.
CATEGORY 2: STEEL RODS (Dangote Steel, Delta Steel)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Dangote Steel | Apapa, Lagos | 9 | 8 | 9 | 9 | 7 | 8.6 | ✓ SELECTED
Delta Steel Products | Surulere, Lagos | 8 | 8 | 8 | 7 | 7 | 7.75 | Not selected
BIS Steel Nigeria | Oshodi, Lagos | 8 | 7 | 8 | 7 | 6 | 7.45 | Not selected
RATIONALE: Best price and SON-certified quality. Consistent grade Y8–Y25 available. Volume discount secured for 7.3 tonnes total.
CATEGORY 3: BLOCKS (Premier Blocks Ltd)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Premier Blocks Ltd | Ojodu, Lagos | 9 | 9 | 9 | 8 | 8 | 8.75 | ✓ SELECTED
Strongblock Nigeria | Ipaja, Lagos | 8 | 8 | 8 | 7 | 7 | 7.75 | Not selected
Afrimass Blocks | Agege, Lagos | 7 | 8 | 7 | 7 | 6 | 7.1 | Not selected
RATIONALE: Premium score (8.80). Delivers to site. Consistent 9" and 6" sizes meeting NIS 87. Best warranty on replacement of defective units.
CATEGORY 4: ROOFING (Alum Roofing Ng)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Alum Roofing Ng | Ikeja, Lagos | 9 | 8 | 8 | 8 | 8 | 8.3 | ✓ SELECTED
Bond Aluminium | Isolo, Lagos | 8 | 8 | 8 | 7 | 7 | 7.75 | Not selected
MetroRoof Nigeria | Agbara, Ogun | 7 | 7 | 8 | 7 | 6 | 7.15 | Not selected
RATIONALE: Best price per sqm at ₦3,800. Delivers factory-direct. 1-year warranty on material defects. 0.55mm gauge confirmed.
CATEGORY 5: TILES (Eleganza)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Eleganza Tiles | Ojodu, Lagos | 8 | 9 | 9 | 8 | 9 | 8.55 | ✓ SELECTED
Porcelain Palace Ng | Victoria Island | 7 | 8 | 9 | 8 | 8 | 7.95 | Not selected
Marshalls Tiles Nigeria | Lekki | 7 | 7 | 8 | 8 | 7 | 7.4 | Not selected
RATIONALE: Highest overall score (8.70). Consistent stock availability, ISO quality, and competitive pricing. Replacement guarantee for breakages.
CATEGORY 6: ELECTRICAL CABLES (Nigerchin)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Nigerchin Cables | Ikeja, Lagos | 9 | 8 | 9 | 8 | 8 | 8.55 | ✓ SELECTED
Coleman Cables Nig. | Lekki, Lagos | 8 | 8 | 9 | 8 | 7 | 8.15 | Not selected
PZ Cables Nigeria | Apapa, Lagos | 8 | 7 | 8 | 7 | 6 | 7.45 | Not selected
RATIONALE: SON-certified. Best price for 2.5mm and 4mm cables. Full stock availability. Technical support on wiring schedule provided.
CATEGORY 7: PLUMBING (Vanguard Pipes)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Vanguard Pipes | Mushin, Lagos | 9 | 9 | 8 | 8 | 8 | 8.5 | ✓ SELECTED
Aquatech Pipes Nig. | Ikeja, Lagos | 8 | 8 | 8 | 8 | 7 | 7.9 | Not selected
Georg Fischer Nig. | V/Island, Lagos | 7 | 7 | 9 | 9 | 9 | 8 | Not selected
RATIONALE: Best price and fastest delivery. uPVC and PPR pipes in all required sizes available in Lagos stock. 3-year fitting warranty.
CATEGORY 8: READY MIX CONCRETE (Lafarge ReadyMix)
Supplier | Location | Price | Lead Time | Quality | Track Record | Warranty | Wtd Score | Decision
Lafarge ReadyMix | Sagamu Rd, Lagos | 8 | 9 | 9 | 9 | 8 | 8.6 | ✓ SELECTED
Readymix Concrete Ng | Oshodi, Lagos | 8 | 8 | 8 | 8 | 7 | 7.9 | Not selected
Dantata & Sawoe | Ikeja, Lagos | 7 | 7 | 8 | 8 | 7 | 7.4 | Not selected
RATIONALE: Best quality assurance. 25N/mm² guaranteed with test cubes. 8-hour SLA on delivery. Most reliable for foundation pour scheduling.

## Professional Fees
PROFESSIONAL FEES & CONSULTANCY COSTS
Regulatory, consultancy, and statutory costs in Nigerian Naira (₦)
TOTAL PROFESSIONAL FEES |  |  |  |  | 5065000
# | Service Description | Service Provider | Basis | Amount (₦) | Notes
PF-01 | Architectural Design & Drawings | Arch. Biodun Adeleke (ARCON Registered) | % of contract | 850000 | Full working drawings, 3D visualization, and specification
PF-02 | Structural Engineering Design | Engr. Chike Okonkwo (COREN Registered) | Lump sum | 650000 | Structural calculations, foundation design, raft slab specification
PF-03 | Quantity Surveying Services | QS Tunde Adesola (NIQS Member) | % of contract | 480000 | BOQ preparation, cost planning, valuation, and final account
PF-04 | Building Plan Approval (LASBCA) | Lagos State Building Control Agency | Statutory fee | 380000 | Approval of building plans per Lagos State Urban Planning Law
PF-05 | Environmental Impact Assessment | Lagos State EPA | Statutory fee | 120000 | EIA report for development in designated zone
PF-06 | Survey & Deed of Assignment | Licensed surveyor — Surveyor Musa Bello | Lump sum | 250000 | Certificate of Occupancy (C of O) processing and survey plan
PF-07 | Project Management Supervision | PM Consultant — Construct-Pro Ltd | Monthly retainer × 18 | 720000 | Monthly site visits, progress reports, contractor management
PF-08 | Soil Investigation / Geotechnical Report | GeoTech Nigeria Ltd | Lump sum | 180000 | Borehole logs, bearing capacity, German floor specification
PF-09 | MEP Engineering (M&E Design) | MEP Consultants Nigeria | Lump sum | 320000 | Mechanical, electrical and plumbing design and specifications
PF-10 | Insurance — Contractor All Risk (CAR) | AXA Mansard Insurance | Annual premium | 285000 | 18-month CAR policy covering materials, plant, and third-party liability
PF-11 | Water Board Connection Approval | Lagos Water Corporation | Statutory fee | 85000 | Water mains connection application and approval
PF-12 | EKEDC Electrical Connection | Eko Electricity Distribution Co. | Statutory fee | 125000 | Meter and service connection to national grid
PF-13 | COREN Certification (Electrical & Civil) | Council for the Regulation of Engineering | Statutory fee | 75000 | Mandatory engineering certification on completion
PF-14 | Final Completion Certificate | LASBCA | Statutory fee | 95000 | Habitation / completion certificate from Lagos State
PF-15 | Procurement Officer Professional Fee | Self (Portfolio Owner) | Lump sum | 450000 | Full procurement management — 18 months: sourcing, tendering, contracting
TOTAL PROFESSIONAL FEES |  |  |  | 5065000

## PO Tracker
PROCUREMENT SCHEDULE & PURCHASE ORDER TRACKER
Live tracking of all material procurement orders ¦ 3-Bedroom Flat Project ¦ 2025
PO No. | Material/Service | Supplier | Phase | Qty | PO Value (₦) | Order Date | Expected Delivery | Actual Delivery | Status | Payment Status
PO-001 | Geotechnical/Soil Investigation | GeoTech Nigeria Ltd | Pre-Construction | 1 lot | 180000 | 05-Jan-2025 | 15-Jan-2025 | 15-Jan-2025 | DELIVERED | PAID
PO-002 | Architectural & Structural Drawings | Arch. Adeleke & Engr. Okonkwo | Pre-Construction | 1 lot | 1500000 | 05-Jan-2025 | 28-Feb-2025 | 28-Feb-2025 | DELIVERED | PAID
PO-003 | LASBCA Building Plan Approval | Lagos State Building Control | Pre-Construction | 1 lot | 380000 | 10-Jan-2025 | 15-Mar-2025 | 15-Mar-2025 | DELIVERED | PAID
PO-004 | Site Clearing & Excavation | Kola Excavators | Phase 1 | 1 | 756000 | 20-Mar-2025 | 25-Mar-2025 | 24-Mar-2025 | DELIVERED | PAID
PO-005 | Anti-Termite Treatment | Termiguard Nig. | Phase 1 | 180 | 216000 | 22-Mar-2025 | 23-Mar-2025 | 23-Mar-2025 | DELIVERED | PAID
PO-006 | Hardcore Supply & Compaction | Suntech Nig. Ltd | Phase 1 | 1 | 461500 | 23-Mar-2025 | 25-Mar-2025 | 25-Mar-2025 | DELIVERED | PAID
PO-007 | BRC Mesh A393 (30 sheets) | Steel Baron Nig. | Phase 1 | 30 | 2550000 | 25-Mar-2025 | 30-Mar-2025 | 30-Mar-2025 | DELIVERED | PAID
PO-008 | Dangote Cement — Batch 1 (200 bags) | Dangote Cement Dist. | Phase 1 | 200 | 1440000 | 26-Mar-2025 | 28-Mar-2025 | 28-Mar-2025 | DELIVERED | PAID
PO-009 | Granite & Sharp Sand — Batch 1 | Apapa Quarry Ltd / Lagos Sand | Phase 1 | 1 | 1650000 | 27-Mar-2025 | 29-Mar-2025 | 29-Mar-2025 | DELIVERED | PAID
PO-010 | Ready Mix Concrete — Raft Slab | Lafarge ReadyMix | Phase 1 | 47 | 2580000 | 01-Apr-2025 | 03-Apr-2025 | 03-Apr-2025 | DELIVERED | PAID
PO-011 | Mild Steel Rods Y16 & Y12 (Foundation) | Dangote Steel | Phase 1 | 1.3 | 845000 | 28-Mar-2025 | 31-Mar-2025 | 31-Mar-2025 | DELIVERED | PAID
PO-012 | DPC Bricks & Damp Proof Membrane | Premier Blocks Ltd / BuildPro | Phase 1 | 1 | 478000 | 01-Apr-2025 | 03-Apr-2025 | 05-Apr-2025 | DELIVERED | PAID
PO-013 | 9-inch Hollow Blocks (4200 units) | Premier Blocks Ltd | Phase 2 | 4200 | 1596000 | 15-Apr-2025 | 20-Apr-2025 | 22-Apr-2025 | DELIVERED | PAID
PO-014 | 6-inch Solid Blocks (3500 units) | Premier Blocks Ltd | Phase 2 | 3500 | 1120000 | 15-Apr-2025 | 20-Apr-2025 | 21-Apr-2025 | DELIVERED | PAID
PO-015 | Dangote Cement — Batch 2 (300 bags) | Dangote Cement Dist. | Phase 2 | 300 | 2160000 | 20-Apr-2025 | 22-Apr-2025 | 23-Apr-2025 | DELIVERED | PAID
PO-016 | Steel Rods Y16, Y12, Y10 (Columns & Beams) | Dangote Steel | Phase 2 | 5.5 | 3575000 | 20-Apr-2025 | 25-Apr-2025 | 26-Apr-2025 | DELIVERED | PAID
PO-017 | Ready Mix Concrete — Ground Floor Slab | Lafarge ReadyMix | Phase 2 | 22.5 | 1237500 | 10-May-2025 | 12-May-2025 | 12-May-2025 | DELIVERED | PAID
PO-018 | Form Work Timber & Plywood (Batch 1) | Timber King Abk | Phase 2 | 1 | 905000 | 05-May-2025 | 08-May-2025 | 09-May-2025 | DELIVERED | PAID
PO-019 | 6-inch Hollow Blocks — 1st Floor (2800) | Premier Blocks Ltd | Phase 3 | 2800 | 868000 | 20-Jun-2025 | 25-Jun-2025 | 27-Jun-2025 | DELIVERED | PAID
PO-020 | Dangote Cement — Batch 3 (150 bags) | Dangote Cement Dist. | Phase 3 | 150 | 1080000 | 20-Jun-2025 | 22-Jun-2025 | 22-Jun-2025 | DELIVERED | PAID
PO-021 | Ready Mix Concrete — First Floor Slab | Lafarge ReadyMix | Phase 3 | 22.5 | 1237500 | 15-Jul-2025 | 17-Jul-2025 | 17-Jul-2025 | DELIVERED | PAID
PO-022 | Steel Rods Y8 (Distribution bars) | Dangote Steel | Phase 3 | 0.8 | 520000 | 15-Jun-2025 | 18-Jun-2025 | 18-Jun-2025 | DELIVERED | PAID
PO-023 | Roofing Timber (Rafters & Purlins) | Timber King Abk | Phase 4 | 1 | 792000 | 01-Aug-2025 | 05-Aug-2025 | 06-Aug-2025 | DELIVERED | PAID
PO-024 | Aluminum Long Span Roofing Sheets | Alum Roofing Ng | Phase 4 | 280 | 1064000 | 01-Aug-2025 | 07-Aug-2025 | 07-Aug-2025 | DELIVERED | PAID
PO-025 | Ridge Caps, Fascia & Gutters | Alum Roofing Ng / RoofPro | Phase 4 | 1 | 598500 | 08-Aug-2025 | 12-Aug-2025 | 13-Aug-2025 | DELIVERED | PAID
PO-026 | All Plumbing Materials (uPVC, PPR, fittings) | Vanguard Pipes | Phase 5 | 1 | 2714000 | 01-Sep-2025 | 10-Sep-2025 | 11-Sep-2025 | DELIVERED | PARTIAL PMT
PO-027 | Bathroom Fittings (WC, basins, showers) | Sanitech Nig. | Phase 5 | 1 | 645000 | 01-Sep-2025 | 10-Sep-2025 |  | ON ORDER | DEPOSIT PAID
PO-028 | Electrical Cables (all gauges) | Nigerchin Cables | Phase 5 | 1 | 1086000 | 01-Sep-2025 | 08-Sep-2025 | 08-Sep-2025 | DELIVERED | PAID
PO-029 | Distribution Board, MCBs & Sockets | Clipsal Nigeria / Schneider | Phase 5 | 1 | 428200 | 05-Sep-2025 | 10-Sep-2025 |  | AWAITING | NOT PAID
PO-030 | Inverter, Batteries & Solar Panels | Victron Energy / Jinko Solar | Phase 5 | 1 | 1472000 | 05-Sep-2025 | 20-Sep-2025 |  | ON ORDER | DEPOSIT PAID
PO-031 | Aluminium Windows (all types) | Alumaco Nig. Ltd | Phase 5 | 20 | 1542000 | 10-Sep-2025 | 25-Sep-2025 |  | ON ORDER | DEPOSIT PAID
PO-032 | Security Doors (main & back) | Ironmax Nig. | Phase 5 | 2 | 660000 | 10-Sep-2025 | 20-Sep-2025 |  | ON ORDER | NOT PAID
PO-033 | Internal & Bathroom Doors | Woodcraft Nig. | Phase 6 | 12 | 742200 | 15-Oct-2025 | 01-Nov-2025 |  | PENDING | NOT PAID
PO-034 | All Floor & Wall Tiles | Eleganza Tiles | Phase 6 | 1 | 3876500 | 01-Nov-2025 | 15-Nov-2025 |  | PENDING | NOT PAID
PO-035 | Tile Adhesive & Grout | Weber Nigeria | Phase 6 | 1 | 534000 | 01-Nov-2025 | 10-Nov-2025 |  | PENDING | NOT PAID
PO-036 | Paints (Dulux Interior & Exterior) | Dulux Nigeria | Phase 6 | 1 | 1562000 | 15-Nov-2025 | 25-Nov-2025 |  | PENDING | NOT PAID
PO-037 | POP Ceiling Boards & Cornices | CeilPro Nig. | Phase 6 | 1 | 1623000 | 15-Nov-2025 | 30-Nov-2025 |  | PENDING | NOT PAID
PO-038 | Staircase Steel & Handrails | SteelFab Nig. | Phase 6 | 1 | 1391000 | 01-Dec-2025 | 20-Dec-2025 |  | PENDING | NOT PAID
PO-039 | Gate, Fence Blocks & Driveway Paving | Ironmax / Premier / Interloc Nig. | Phase 6 | 1 | 3659000 | 01-Jan-2026 | 28-Feb-2026 |  | PENDING | NOT PAID
PO-040 | Borehole Drilling & Water System | Aqua Drill Nig. | Phase 6 | 1 | 1200000 | 15-Jan-2026 | 01-Mar-2026 |  | PENDING | NOT PAID
TOTAL COMMITTED PROCUREMENT VALUE |  |  |  |  | 52924900
TOTAL POs ISSUED |  |  | DELIVERED |  |  | ON ORDER / PENDING |  |  | PAID
40 |  |  | 27 |  |  | 12 |  |  | 26

## Budget Summary
PROJECT BUDGET SUMMARY & COST ANALYSIS
3-Bedroom Flat ¦ German Floor Foundation ¦ Lagos, Nigeria ¦ All figures in ₦
MATERIALS COST | LABOUR COST | PROFESSIONAL FEES | CONTINGENCY (10%) | GRAND TOTAL
63574700 | 49765000 | 0 | 11333970 | 124673670
₦ | ₦ | ₦ | ₦ | ₦
BUDGET BREAKDOWN BY CONSTRUCTION PHASE
Phase | Description | Materials (₦) | Labour (₦) | Total (₦) | % of Budget
Phase 1 | Site Preparation & German Floor Foundation | 3392000 | 825000 | 4217000 | 9.295%
Phase 2 | Ground Floor Superstructure (Block, Concrete, Steel) | 7255000 | 1980000 | 9235000 | 20.36%
Phase 3 | First Floor Superstructure | 5620000 | 1820000 | 7440000 | 16.4%
Phase 4 | Roofing Works | 3491500 | 760000 | 4251500 | 9.371%
Phase 5 | MEP (Plumbing, Electrical, Solar) | 6345200 | 1380000 | 7725200 | 17.03%
Phase 6 | Finishing (Tiling, Painting, Doors, Fencing) | 9850000 | 2650000 | 12500000 | 27.55%
TOTAL (excl. Fees & Contingency) |  | 35953700 | 9415000 | 45368700
PROCUREMENT STRATEGY HIGHLIGHTS
Competitive Tendering | All major materials (cement, steel, concrete, tiles) subjected to minimum 3-quote process. Lowest compliant bid selected. |  |  | ₦ Savings: ~₦4.2M (vs. highest quotes)
Framework Agreements | Cement (650 bags @ ₦7,200), Blocks (10,500 units), Steel (7.3 tonnes) — locked-in unit rates with approved suppliers. |  |  | Risk mitigation: Price inflation protection
Staged Procurement | Materials procured phase-by-phase to avoid over-stocking, reduce storage risk, and optimize cash flow. |  |  | Cash flow: Avoids ₦15M+ upfront capital tie-up
Local Sourcing Priority | 70% of materials sourced within 30km of site (Lagos metropolis). Reduces transport cost & lead time significantly. |  |  | Logistics savings: ~₦850,000 estimated
Vendor Pre-Qualification | All vendors verified: CAC registration, SON certification, bank statements, and site visit references required. |  |  | Quality assurance: Zero non-conforming deliveries to date
PO Documentation | 100% of purchases covered by formal Purchase Orders with delivery terms, inspection, and payment milestones. |  |  | Compliance: Full audit trail for all transactions